## Issue Tracker
Fixed? (Y/N) | Category | Title | Description | Priority | Jira Reference #
Yes | Logic | Skip logic | Verify skip logic works |  | 4
Yes | Pages | Landing page B and C | Landing page B and C don't exist |  | 12
Yes | Pages | Q1c | Missing |  | 12
No | Pages | Q24 | Verify Male/Female options
No | Pages | QD version for abbreviated qx | See abbreviated questionnaire spec for QD wording for the abbreviated qx |  | 12
No | Pages | QE | Verify QE - can't access yet |  | 12
No | Progress Bar | Progress bar 100% | Progress bar shouldn't show 100% until on the summary page |  | 3
No | Progress Bar | Progress bar for abbreviated Qx | Progress bar should scale accordingly for the abbreviated questionnaire, not start at 94% for the first question
No | Text Edits | Q16-Q17 | Tab certain things over See mock-up on Mock-Ups tab |  | 3
No | Text Edits | Q17 | Change text to "In the last 4 weeks…" by adding the … |  | 3
No | Text Edits | Landing page text | Change email address to "neuroSHARE@Sutterhealth.org" | Spec error | 12
No | Text Edits | Q22 question text | Spec error - change to "In general, how often do you wake up feeling rested in the morning?" | Spec error | 12
No | Text Edits | Q25 question text | Spec error - change text and add radio buttons + numbers to scale See mock-up on Mock-Ups tab | Spec error | 12
No | Text Edits | Q26 question text | Spec error - change text and add radio buttons + numbers + smiley faces to scale See mock-up on Mock-Ups tab | Spec error | 12
No | Text Edits | Q27 response text | Change response text to "I've had relapses on these dates (enter up to 6 dates)" "Number of relapses:" + dropdown See mock-up on Mock-Ups tab |  | 12
No | Text Edits | Q5 response text | Spec error - change 3rd response option to "I have to make some effort to raise it" | Spec error | 12
No (see mocks) | Text Edits | Q6 response text | Spec error - remove the "Stiffness and spasms…" banner over the last 4 response options See mock-up on Mock-Ups tab | Spec error | 12
No | Text Edits | QD question text | Bold "Click…" sentence | Spec error | 12
No | UI Elements | Dropdown appearance | Make dropdowns more visually distinct - outline or darker background? |  | 3
No | UI Elements | Q27 dropdown size | Q27 - Make month dropdown smaller |  | 3
Yes | UI Elements | Page resizing | Verify pages resize dynamically |  | 3
No(see mocks) | UI Elements | Smiley face scale | Q26 - missing smiley face scale? Was there an issue implementing this? |  | 12
No | UI Elements | Yellow accent color | Change yellow to something darker - either black or purple? |  | 3
No | Text Edits | Q1b response text | In the answers section, change "899"--> "900" , Change "599" --> "600"
No | UI Elements | Page resize minimum | 980 x 600 px
No | Logic | Close button redirect | Clicking the close button will redirect page to https://www.sutterhealth.org/
No | Text Edits | Q1a intro text | Change page 1a intro text to "The first set of questions ask about symptoms that you may have. Each person has a different experience with MS, so you may not have – or ever have – all of the symptoms we ask about. Please do your best to pick an answer from the choices that are offered. You may skip any questions you don’t want to answer. Just keep in mind that we may not be able to calculate your EDSS score if you skip questions." See mock-up on Mock-Ups tab | Spec error

## Mock-Ups
Q1a
Q6
Q16-Q17
Q25
Q26
Q27