## Issue Tracker
Fixed? (Y/N) | Category | Title | Description | Priority | Jira Reference #
No | UI Elements | All font | Verify font size is at least size 14
No | UI Elements | All questions and responses spacing | Decrease white space between questions and associated responses When there are multiple questions on a page, increase the white space between the last response of the previous question and the question text See mock-up on the Mock-Ups tab | Spec error
No | Text Edits | All response options puncuation | For all response options, remove periods at the very end of the response (Q7 Response option 1-3, Q10 R1-5, Q13 R4, Q21 R3-4)
No | UI Elements | All tables: far left column | Fit left column to text - make smaller when possible Left align text in far left column
Yes | Logic | Close button redirect | Clicking the close button will redirect page to https://www.sutterhealth.org/
Yes | UI Elements | Dropdown appearance | Make dropdowns more visually distinct - outline or darker background? |  | 3
Yes | Pages | Landing page B and C | Landing page B and C don't exist |  | 12
Yes | Text Edits | Landing page text | Change email address to "neuroSHARE@Sutterhealth.org" | Spec error | 12
No | Text Edits | Landing page text pt2 | Change date format to "September 2, 2018" Change text to "Please email neuroSHARE@Sutterhealth.org if you have any questions about the questionnaire. Thank you in advance for your time." | Spec error
No | UI Elements | Page resize minimum | 980 x 600 px
No | UI Elements | Page resizing | Verify pages resize dynamically in internet explorer (verify Q20, Q21) |  | 3
Yes | Progress Bar | Progress bar 100% | Progress bar shouldn't show 100% until on the summary page |  | 3
Yes | Progress Bar | Progress bar for abbreviated Qx | Progress bar should scale accordingly for the abbreviated questionnaire, not start at 94% for the first question
No | Text Edits | Q13, Q14 response options | In the answers section, capitalize NOT for the first response option | Spec error
No | Text Edits | Q16-Q17 | Tab certain things over See mock-up on Mock-Ups tab |  | 3
Yes | Text Edits | Q17 | Change text to "In the last 4 weeks…" by adding the … |  | 3
Yes | Text Edits | Q1a intro text | Change page 1a intro text to "The first set of questions ask about symptoms that you may have. Each person has a different experience with MS, so you may not have – or ever have – all of the symptoms we ask about. Please do your best to pick an answer from the choices that are offered. You may skip any questions you don’t want to answer. Just keep in mind that we may not be able to calculate your EDSS score if you skip questions." See mock-up on Mock-Ups tab | Spec error
Yes | Text Edits | Q1b response text | In the answers section, change "899"--> "900" , Change "599" --> "600"
Yes | Pages | Q1c | Missing |  | 12
No | Text Edits | Q20 response options | Capitalize NO in first response Change text from "I have some concentration and memory problems, or problems with coping with stress, but I am able to handle my daily routines including completing this survey" to "I have some concentration and memory problems, or problems with coping with stress. But I am able to handle my daily routines including completing this survey" Change text from "I have problems with concentration and memory that my friends and family notice; this is beginning to affect my daily routine. It makes completing this survey difficult" to "I have problems with concentration and memory that my friends and family notice. This is beginning to affect my daily routine. It makes completing this survey difficult" Change text from "I have severe impairment in my cognitive (thinking) abilities; for example, I sometimes forget where I am and who I am talking to. I need help completing this survey" to "I have severe impairment in my cognitive thinking abilities. For example, I sometimes forget where I am and who I am talking to. I need help completing this survey" Change text from "I have no meaningful conversation and am unable to handle my affairs because of my severe cognitive problems. I need someone else to complete this survey" to "I have no meaningful conversation and am unable to handle my affairs because of my severe cognitive problems; I need someone else to complete this survey" | Spec error
No | Text Edits | Q21 response options | Capitalize NO in first response Change text from "Due to my fatigue I have to rest unusually often; this affects less than half of my daily activities. I often cannot complete my daily routine without naps or significant rest" to "Due to my fatigue I have to rest unusually often. This affects less than half of my daily activities. I often cannot complete my daily routine without naps or significant rest" Change text from "I experience severe fatigue levels that have overtaken my life; I am unable to complete more than half of my daily tasks" to "I experience severe fatigue levels that have overtaken my life. I am unable to complete more than half of my daily tasks" In answer section for the second question, only capitalize the first letter of each response option (for example, "All of the time", "Most of the time", etc.) | Spec error
Yes | Text Edits | Q22 question text | Spec error - change to "In general, how often do you wake up feeling rested in the morning?" | Spec error | 12
No | Pages | Q24 | Verify Male/Female options
No | Logic | Q25 logic | Max of 6 relapse responses. Currently shows 8
No | Text Edits | Q25 question text | Spec error - change text and add radio buttons + numbers to scale Change text to "In general, how much pain are you in? Select one number from the scale below:" See mock-up on Mock-Ups tab | Spec error | 12
No | UI Elements | Q25 text placement | Move text and remove outline around boxes of text See mock-up on Mock-Ups tab | Spec error
No | Text Edits | Q26 question text | Spec error - change text and add radio buttons + numbers + smiley faces to scale Change text to "Overall, how would you rate your own quality-of-life? Select one number from the scale below:" See mock-up on Mock-Ups tab | Spec error | 12
No | UI Elements | Q26 text placement | Move text and remove outline around boxes of text See mock-up on Mock-Ups tab | Spec error
No | UI Elements | Q27 dropdown size | Q27 - Make month dropdown smaller |  | 3
No | Text Edits | Q27 question text | Change text to "This question asks about relapses." "The symptoms might be new or significantly worse than before" | Spec error
Yes | Text Edits | Q27 response text | Change response text to "I've had relapses on these dates (enter up to 6 dates)" "Number of relapses:" + dropdown See mock-up on Mock-Ups tab |  | 12
No | Text Edits | Q27 response text pt2 | Change text to "I've had relapses" Change month options to actual written out months (for example, January, February, etc.) | Spec error
No | UI Elements | Q27 spacing | Add more spaces between the bullet points
No | UI Elements | Q29 checkbox color | Change filled in checkbox to purple
No | UI Elements | Q29 comment box | Make comment box longer on default
No | Text Edits | Q29 question text | Change text to "Please select any topics you'd like to discuss at your next appointment." | Spec error
No | Text Edits | Q29 response text | Change text to "Other topic" Remove "Other topics?" text in comment box and replace with "Enter text here" | Spec error
Yes | Text Edits | Q5 response text | Spec error - change 3rd response option to "I have to make some effort to raise it" | Spec error | 12
Yes | Text Edits | Q6 response text | Spec error - remove the "Stiffness and spasms…" banner over the last 4 response options See mock-up on Mock-Ups tab | Spec error | 12
No | Text Edits | Q8 response text | Change left column text to "Your arm(s)" and "Your leg(s)" by removing the question mark | Spec error
Yes | Text Edits | QD question text | Bold "Click…" sentence | Spec error | 12
Yes | Pages | QD version for abbreviated qx | See abbreviated questionnaire spec for QD wording for the abbreviated qx |  | 12
Yes | Pages | QE | Verify QE - can't access yet |  | 12
No |  | Review page logic | Pull and display number of relapses in the review page | Spec error
No |  | Review page text | Put symptom and status info in bullet point list like "Vision (mild)" Change text to "Current symptoms with status:" "Topics you want to discuss with your doctor:" "Other topics:" "Click submit questionnaire to send these responses to your doctor." Add 3rd bullet point "Relapses since your last visit:" Bold "Lareco, here is a summary of information" See mock-up on Mock-Ups tab | Spec error
Yes | Logic | Skip logic | Verify skip logic works |  | 4
No | UI Elements | Smiley face scale | Q26 - missing smiley face scale? Was there an issue implementing this? |  | 12
No | UI Elements | Yellow accent color | Change yellow to purple Make circle fill AND outline purple |  | 3

## Mock-Ups
All questions and responses spacing
Q1a
Q6
Q16-Q17
Q25
Q26
Q27
Review page